## Summary
QA Regression Report - NU-AURA Platform
Report Date | 2026-03-22 16:08
QA Type | Post-Fix Regression Sweep
Tester | Automated QA (Claude)
Accounts Tested | Fayaz M (SUPER_ADMIN), Sumit Kumar (MANAGER), Gokul R (TEAM_LEAD), Saran V (EMPLOYEE)
METRIC | VALUE
Total Routes Tested | 51
Routes Passing | 43
Routes Failing | 4
Routes Skipped/Phase 2 | 4
Pass Rate | 84.3% (91.5% excl. Phase 2)
New Bugs Found | 4
Fixed in This Session | 2
Remaining (Skipped/Deferred) | 2
Critical | 0
High | 1 (Fixed)
Medium | 2 (1 Skipped-Phase2, 1 Fixed)
Low | 1 (Deferred)
Previous Bugs Fixed (V66 + Frontend) | 19
Previous Bugs Regressed | 0
Regression Rate | 0%
RBAC Boundary Tests | VALUE
Employee -> /admin blocked | PASS
Employee -> /admin/roles blocked | PASS
Employee -> /payroll (SELF scope) | PASS
Employee -> /employees (SELF scope) | PASS
Employee -> /leave (SELF scope) | PASS
Team Lead -> /performance | PASS
Team Lead -> /training | PASS
Team Lead -> /surveys | PASS
Manager -> /recruitment | PASS
Manager -> /contracts | PASS
SUB-APP BREAKDOWN | Tested | Pass | Fail | Notes
NU-HRMS | 29 | 28 | 1 | leave-requests/status 500 on dashboard
NU-Hire | 5 | 5 | 0 | All routes functional
NU-Grow | 8 | 8 | 0 | All routes functional after V66 RBAC fix
NU-Fluence | 4 | 0 | 4 | Phase 2 - backend Elasticsearch dependency
RBAC Boundary | 5 | 5 | 0 | All access control working correctly

## Bug Report
Bug ID | Sub-App | Module | Page Route | Bug Type | Severity | Description | Expected Behavior | Actual Behavior | Steps to Reproduce | Console Log | Failed API Endpoint | Screenshot Path | Component File Path | Fix Status | Fix Notes
BUG-001 | NU-HRMS | Dashboard | /me/dashboard | Network | High | Leave requests status API returns 500 error on My Dashboard page | GET /api/v1/leave-requests/status/ should return leave request status data | API returns HTTP 500 Internal Server Error | 1. Login as any user 2. Navigate to /me/dashboard 3. Check network tab | GET /api/v1/leave-requests/status/?page=0&size=10 500 | GET /api/v1/leave-requests/status/?page=0&size=10 -> 500 |  | backend/src/main/java/**/controller/LeaveRequestController.java | Fixed | Added enabled: !!status guard to useLeaveRequestsByStatus hook - prevents empty status API call
BUG-002 | NU-Fluence | Wiki/Blogs/Wall | /fluence/* | Network | Medium | All Fluence backend APIs return 500 - wiki, blogs, wall, dashboard non-functional | Fluence API endpoints should return data or empty results | All /api/v1/fluence/* endpoints return HTTP 500. Elasticsearch connectivity issue. | 1. Login as any user 2. Navigate to /fluence/wiki 3. Check network tab | Multiple 500 errors on /api/v1/fluence/* endpoints | GET /api/v1/fluence/wiki/spaces, /pages, /blog/posts -> all 500 |  | backend + Elasticsearch config | Skipped | Phase 2 module - requires Elasticsearch 8.11.0 running
BUG-003 | NU-Fluence | Navigation | /fluence/blogs | Console | Medium | MobileBottomNav has duplicate React key for /fluence/wiki | Each navigation item should have a unique key prop | Console: "Encountered two children with the same key /fluence/wiki" | 1. Navigate to any /fluence/* page 2. Check console | Warning: Encountered two children with the same key `/fluence/wiki` |  |  | frontend/components/layout/MobileBottomNav.tsx:53 | Fixed | Changed Fluence Home href from /fluence/wiki to /fluence/dashboard to avoid duplicate key
BUG-004 | Platform | LinkedIn | /me/dashboard | Network | Low | LinkedIn posts API returns 500 - backend endpoint not fully implemented | GET /api/v1/linkedin-posts/active should return data or empty results | Returns HTTP 500. Frontend gracefully handles (no user-visible error). | 1. Login 2. Navigate to /me/dashboard 3. Check network tab | GET /api/v1/linkedin-posts/active 500 (handled gracefully) | GET /api/v1/linkedin-posts/active -> 500 |  | backend/src/main/java/**/controller/LinkedInController.java | Deferred | Backend endpoint not connected. Frontend catches gracefully.

## Pages Tested
Route | Sub-App | Module | Test Role | Status | Bug Count | Notes
/me/dashboard | NU-HRMS | Dashboard | SUPER_ADMIN | Fail | 1 | leave-requests/status 500
/me/profile | NU-HRMS | Profile | SUPER_ADMIN | Pass | 0
/employees | NU-HRMS | Employees | SUPER_ADMIN | Pass | 0
/departments | NU-HRMS | Departments | SUPER_ADMIN | Pass | 0
/attendance | NU-HRMS | Attendance | SUPER_ADMIN | Pass | 0
/leave | NU-HRMS | Leave | SUPER_ADMIN | Pass | 0
/payroll | NU-HRMS | Payroll | SUPER_ADMIN | Pass | 0
/compensation | NU-HRMS | Compensation | SUPER_ADMIN | Pass | 0
/benefits | NU-HRMS | Benefits | SUPER_ADMIN | Pass | 0
/expenses | NU-HRMS | Expenses | SUPER_ADMIN | Pass | 0
/loans | NU-HRMS | Loans | SUPER_ADMIN | Pass | 0
/travel | NU-HRMS | Travel | SUPER_ADMIN | Pass | 0
/assets | NU-HRMS | Assets | SUPER_ADMIN | Pass | 0
/letters | NU-HRMS | Letters | SUPER_ADMIN | Pass | 0
/helpdesk | NU-HRMS | Helpdesk | SUPER_ADMIN | Pass | 0
/approvals | NU-HRMS | Approvals | SUPER_ADMIN | Pass | 0
/announcements | NU-HRMS | Announcements | SUPER_ADMIN | Pass | 0
/org-chart | NU-HRMS | Org Chart | SUPER_ADMIN | Pass | 0
/timesheets | NU-HRMS | Timesheets | SUPER_ADMIN | Pass | 0
/projects | NU-HRMS | Projects | SUPER_ADMIN | Pass | 0
/admin | NU-HRMS | Admin Dashboard | SUPER_ADMIN | Pass | 0
/admin/roles | NU-HRMS | Admin Roles | SUPER_ADMIN | Pass | 0
/admin/permissions | NU-HRMS | Admin Permissions | SUPER_ADMIN | Pass | 0
/settings | NU-HRMS | Settings | SUPER_ADMIN | Pass | 0
/reports | NU-HRMS | Reports | SUPER_ADMIN | Pass | 0
/analytics | NU-HRMS | Analytics | SUPER_ADMIN | Pass | 0
/calendar | NU-HRMS | Calendar | SUPER_ADMIN | Pass | 0
/nu-calendar | NU-HRMS | NU Calendar | SUPER_ADMIN | Pass | 0
/nu-drive | NU-HRMS | NU Drive | SUPER_ADMIN | Pass | 0
/recruitment | NU-Hire | Recruitment | MANAGER | Pass | 0
/onboarding | NU-Hire | Onboarding | MANAGER | Pass | 0
/preboarding | NU-Hire | Preboarding | MANAGER | Pass | 0
/offboarding | NU-Hire | Offboarding | MANAGER | Pass | 0
/careers | NU-Hire | Careers | MANAGER | Pass | 0
/performance | NU-Grow | Performance | TEAM_LEAD | Pass | 0
/okr | NU-Grow | OKR | TEAM_LEAD | Pass | 0
/feedback360 | NU-Grow | Feedback 360 | TEAM_LEAD | Pass | 0
/training | NU-Grow | Training | TEAM_LEAD | Pass | 0
/learning | NU-Grow | Learning | TEAM_LEAD | Pass | 0
/recognition | NU-Grow | Recognition | TEAM_LEAD | Pass | 0
/surveys | NU-Grow | Surveys | TEAM_LEAD | Pass | 0
/wellness | NU-Grow | Wellness | TEAM_LEAD | Pass | 0
/fluence/wiki | NU-Fluence | Wiki | TEAM_LEAD | Fail | 1 | Backend 500 - ES dependency
/fluence/blogs | NU-Fluence | Blogs | TEAM_LEAD | Fail | 1 | Backend 500 + dup key
/fluence/wall | NU-Fluence | Wall | TEAM_LEAD | Fail | 1 | Backend 500
/fluence/dashboard | NU-Fluence | Dashboard | TEAM_LEAD | Fail | 1 | Backend 500
/admin [EMPLOYEE] | RBAC | Admin Guard | EMPLOYEE | Pass | 0 | Blocked correctly
/admin/roles [EMPLOYEE] | RBAC | Admin Guard | EMPLOYEE | Pass | 0 | Blocked correctly
/payroll [EMPLOYEE] | RBAC | Self Scope | EMPLOYEE | Pass | 0 | SELF scope working
/employees [EMPLOYEE] | RBAC | Self Scope | EMPLOYEE | Pass | 0 | SELF scope working
/leave [EMPLOYEE] | RBAC | Self Scope | EMPLOYEE | Pass | 0 | Can request leave

## RBAC Matrix
Route/Module | SUPER_ADMIN | HR_ADMIN | MANAGER | TEAM_LEAD | EMPLOYEE | HR_MANAGER | RECRUITMENT_ADMIN
/admin/* | Full | Full | Blocked | Blocked | Blocked | Full | Blocked
/employees | ALL | ALL | TEAM | TEAM | SELF | ALL | ALL
/departments | ALL | ALL | TEAM | TEAM | SELF | ALL | ALL
/attendance | ALL | ALL | TEAM | TEAM | SELF | ALL | SELF
/leave | ALL | ALL | TEAM | TEAM | SELF | ALL | SELF
/payroll | ALL | ALL | SELF | SELF | SELF | ALL | SELF
/performance | ALL | ALL | TEAM | TEAM | SELF | ALL | SELF
/recruitment | ALL | ALL | TEAM | TEAM | N/A | ALL | ALL
/training | ALL | ALL | TEAM | TEAM | SELF | ALL | SELF
/contracts | ALL | ALL | TEAM | TEAM | N/A | ALL | N/A

## Previous Fix Summary
Metric | Value
Previous QA Report | qa-regression-5account-2026-03-22.xlsx
Total Bugs in Previous Report | 19
Bugs Fixed | 19
Bugs Regressed | 0
Fix Rate | 100%
Regression Rate | 0%
Fix Categories | Count
V66 Flyway Migration (RBAC permissions) | 12
Frontend Security Fix (admin layout) | 1
Frontend Hydration Fix (Header/Sidebar) | 2
Frontend PermissionGate Fix (Fluence blogs) | 1
WebSocket Reconnection Fix | 1
React Query Optimization | 1
LinkedIn Service Error Handling | 1
Key Files Modified
V66__fix_rbac_permission_gaps.sql | NEW - 717 lines
frontend/app/admin/layout.tsx | MODIFIED
frontend/components/layout/Header.tsx | MODIFIED
frontend/components/ui/Sidebar.tsx | MODIFIED
frontend/app/fluence/blogs/page.tsx | MODIFIED
frontend/lib/contexts/WebSocketContext.tsx | MODIFIED
frontend/lib/hooks/queries/useAdmin.ts | MODIFIED
frontend/lib/services/linkedin.service.ts | MODIFIED