## Summary
NU-AURA QA Deep Regression Report
Metric | Value
QA Run Date | 2026-03-22 18:22:40
Roles Tested | SuperAdmin
Total Pages Tested | 53
Pages Passed | 47
Pages Failed | 6
Pass Rate | 88.7%
Total Bugs Found | 7
Bugs by Severity | Count
Critical | 1
High | 3
Medium | 3
Low | 0
Status | Note
SuperAdmin Regression | COMPLETE — 51 routes tested
Team Lead Regression | PARTIAL — Backend went 503 after 2 routes
Employee Regression | PENDING — Backend down
V67 Migration | READY — Awaiting backend restart for Flyway

## Bug Report
Bug ID | Sub-App | Module | Page Route | Bug Type | Severity | Description | Expected Behavior | Actual Behavior | Steps to Reproduce | Console Log | Failed API Endpoint | Component File Path | Fix Status | Fix Notes
BUG-001 | NU-HRMS | Dashboard | /dashboard | Network | Medium | LinkedIn posts API returns 500 on dashboard load | LinkedIn posts widget loads or gracefully handles no data | GET /api/v1/linkedin-posts/active returns 500 (repeated 4 times) | 1. Login as SuperAdmin 2. Navigate to /dashboard 3. Observe error | [ApiClient] Error: GET /linkedin-posts/active 500 | /api/v1/linkedin-posts/active (500) | frontend/app/dashboard/page.tsx | Open
BUG-002 | NU-HRMS | People | /org-chart | Network | High | Employee directory search API returns 500 on org-chart page | Org chart loads employee hierarchy successfully | POST /api/v1/employees/directory/search returns 500 | 1. Login as SuperAdmin 2. Navigate to /org-chart 3. Observe error | [ApiClient] Error: POST /employees/directory/search 500 | /api/v1/employees/directory/search (500) | frontend/app/org-chart/page.tsx | Open
BUG-003 | NU-HRMS | People | /approvals/inbox | Network | High | Workflow inbox API returns 500 when loading pending approvals | Approvals inbox loads with pending approval tasks | GET /api/v1/workflow/inbox?status=PENDING returns 500 | 1. Login as SuperAdmin 2. Navigate to /approvals/inbox 3. Observe error |  | /api/v1/workflow/inbox?status=PENDING (500) | frontend/app/approvals/inbox/page.tsx | Open
BUG-004 | NU-HRMS | Expenses | /expenses | Network | High | Expenses employees API returns 500 | Expenses page loads employee expense data | GET /api/v1/expenses/employees/ returns 500 | 1. Login as SuperAdmin 2. Navigate to /expenses 3. Observe error | [ApiClient] Error: GET /expenses/employees/ 500 | /api/v1/expenses/employees/ (500) | frontend/app/expenses/page.tsx | Open
BUG-005 | NU-HRMS | Admin | /admin/users | Console | Medium | Hydration mismatch on admin/users page - SSR/client UI divergence | Page renders without hydration errors | React throws hydration error: initial UI does not match server render | 1. Login as SuperAdmin 2. Navigate to /admin/users 3. Observe error | Error: Hydration failed because the initial UI does not match what was rendered on the server |  | frontend/app/admin/users/page.tsx | Open
BUG-006 | NU-Grow | Performance | /performance | Network | Critical | Team Lead gets 403 on /api/v1/goals - missing REVIEW:VIEW permission (V67 needed) | Team Lead can view performance goals for their team | GET /api/v1/goals returns 403, GET /api/v1/review-cycles/active returns 403 | 1. Login as Team Lead (Mani S) 2. Navigate to /performance 3. Observe 403 on goals + review-cycles APIs | [ApiClient] Error: GET /goals 403; GET /review-cycles/active 403 | /api/v1/goals (403), /api/v1/review-cycles/active (403) | backend: GoalController, ReviewCycleController require REVIEW:VIEW | Fix Ready (V67 migration)
BUG-007 | NU-HRMS | Layout | /leave | Console | Medium | Sidebar SSR hydration mismatch: background-image:var(--sidebar-gradient) exists on server but not client | Sidebar renders without hydration errors | Server has background-image:var(--sidebar-gradient) in style, client does not | 1. Login as SuperAdmin 2. Navigate to /leave 3. Observe error | Warning: Prop style did not match. Server has background-image:var(--sidebar-gradient) |  | frontend/components/ui/Sidebar.tsx | Open

## Pages Tested
Route | Sub-App | Module | Role | Status | Bug Count | Notes | Failed APIs | Console Errors
/feedback360 | NU-Grow | Feedback360 | SuperAdmin | Pass | 0 | Loaded without API errors
/okr | NU-Grow | OKR | SuperAdmin | Pass | 0 | Loaded without API errors
/performance | NU-Grow | Performance | SuperAdmin | Pass | 0 | Loaded without API errors
/recognition | NU-Grow | Recognition | SuperAdmin | Pass | 0 | Loaded without API errors
/surveys | NU-Grow | Surveys | SuperAdmin | Pass | 0 | Loaded without API errors
/training | NU-Grow | Training | SuperAdmin | Pass | 0 | Loaded without API errors
/wellness | NU-Grow | Wellness | SuperAdmin | Pass | 0 | Loaded without API errors
/admin/audit-logs | NU-HRMS | Admin | SuperAdmin | Pass | 0 | Loaded without API errors
/admin/integrations | NU-HRMS | Admin | SuperAdmin | Pass | 0 | Loaded without API errors
/admin/roles | NU-HRMS | Admin | SuperAdmin | Pass | 0 | All APIs 200
/admin/settings | NU-HRMS | Admin | SuperAdmin | Pass | 0 | Loaded without API errors
/admin/users | NU-HRMS | Admin | SuperAdmin | Fail | 1 | Hydration mismatch, APIs all 200 |  | Hydration failed SSR/client mismatch
/analytics | NU-HRMS | Analytics | SuperAdmin | Pass | 0 | All APIs 200
/analytics/org-health | NU-HRMS | Analytics | SuperAdmin | Pass | 0 | Loaded without API errors
/assets | NU-HRMS | Assets | SuperAdmin | Pass | 0 | All APIs 200
/attendance | NU-HRMS | Attendance | SuperAdmin | Pass | 0 | All APIs 200
/benefits | NU-HRMS | Benefits | SuperAdmin | Pass | 0 | All APIs 200
/nu-calendar | NU-HRMS | Calendar | SuperAdmin | Pass | 0 | All APIs 200
/compensation | NU-HRMS | Compensation | SuperAdmin | Pass | 0 | All APIs 200
/dashboard | NU-HRMS | Dashboard | SuperAdmin | Fail | 1 | Page loads but linkedin-posts API 500 | /api/v1/linkedin-posts/active (500) | GET /linkedin-posts/active 500
/dashboards/executive | NU-HRMS | Dashboard | SuperAdmin | Pass | 0 | All APIs 200, no console errors
/nu-drive | NU-HRMS | Drive | SuperAdmin | Pass | 0 | Loaded without API errors
/expenses | NU-HRMS | Expenses | SuperAdmin | Fail | 1 | expenses/employees API 500 | /api/v1/expenses/employees/ (500) | GET /expenses/employees/ 500
/contracts | NU-HRMS | HR Operations | SuperAdmin | Pass | 0 | Loaded without API errors
/helpdesk | NU-HRMS | Helpdesk | SuperAdmin | Pass | 0 | Loaded without API errors
/leave | NU-HRMS | Leave | SuperAdmin | Pass | 0 | All APIs 200
/letters | NU-HRMS | Letters | SuperAdmin | Pass | 0 | All APIs 200
/loans | NU-HRMS | Loans | SuperAdmin | Pass | 0 | Loaded without API errors
/nu-mail | NU-HRMS | Mail | SuperAdmin | Pass | 0 | Loaded without API errors
/me/attendance | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Loaded without API errors
/me/dashboard | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Dashboard loads with all widgets
/me/documents | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Loaded without API errors
/me/leaves | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Loaded without API errors
/me/payslips | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Loaded without API errors
/me/profile | NU-HRMS | My Space | SuperAdmin | Pass | 0 | Loaded without API errors
/payroll | NU-HRMS | Payroll | SuperAdmin | Pass | 0 | All APIs 200
/announcements | NU-HRMS | People | SuperAdmin | Pass | 0 | All APIs 200
/approvals/inbox | NU-HRMS | People | SuperAdmin | Fail | 1 | workflow/inbox API 500 | /api/v1/workflow/inbox?status=PENDING (500)
/departments | NU-HRMS | People | SuperAdmin | Pass | 0 | All APIs 200
/employees | NU-HRMS | People | SuperAdmin | Pass | 0 | All APIs 200
/employees/directory | NU-HRMS | People | SuperAdmin | Pass | 0 | All APIs 200
/org-chart | NU-HRMS | People | SuperAdmin | Fail | 1 | directory/search API 500 | /api/v1/employees/directory/search (500) | POST /employees/directory/search 500
/projects | NU-HRMS | Projects | SuperAdmin | Pass | 0 | All APIs 200
/reports | NU-HRMS | Reports | SuperAdmin | Pass | 0 | Loaded without API errors
/settings | NU-HRMS | Settings | SuperAdmin | Pass | 0 | Loaded without API errors
/statutory | NU-HRMS | Statutory | SuperAdmin | Pass | 0 | Loaded without API errors
/tax | NU-HRMS | Tax | SuperAdmin | Pass | 0 | Loaded without API errors
/travel | NU-HRMS | Travel | SuperAdmin | Pass | 0 | Loaded without API errors
/offboarding | NU-Hire | Offboarding | SuperAdmin | Pass | 0 | Loaded without API errors
/onboarding | NU-Hire | Onboarding | SuperAdmin | Pass | 0 | Loaded without API errors
/recruitment | NU-Hire | Recruitment | SuperAdmin | Pass | 0 | Loaded without API errors
/performance | NU-Grow | Performance | TeamLead | Fail | 1 | goals+review-cycles 403 - needs REVIEW:VIEW | /api/v1/goals (403); /api/v1/review-cycles/active (403) | GET /goals 403
/me/dashboard | NU-HRMS | My Space | TeamLead | Pass | 0 | Dashboard loaded clean

## RBAC Matrix
Route | Sub-App | Module | SuperAdmin | TeamLead Expected | TeamLead Actual | Employee Expected | Employee Actual
/admin/audit-logs | NU-HRMS | Admin | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/admin/integrations | NU-HRMS | Admin | Pass | — | Not Tested | — | Not Tested
/admin/roles | NU-HRMS | Admin | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/admin/settings | NU-HRMS | Admin | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/admin/users | NU-HRMS | Admin | Fail | BLOCKED | Not Tested | BLOCKED | Not Tested
/analytics | NU-HRMS | Analytics | Pass | — | Not Tested | — | Not Tested
/analytics/org-health | NU-HRMS | Analytics | Pass | — | Not Tested | — | Not Tested
/announcements | NU-HRMS | People | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/approvals/inbox | NU-HRMS | People | Fail | ALLOWED | Not Tested | ALLOWED | Not Tested
/assets | NU-HRMS | Assets | Pass | ALLOWED | Not Tested | — | Not Tested
/attendance | NU-HRMS | Attendance | Pass | ALLOWED | Not Tested | — | Not Tested
/benefits | NU-HRMS | Benefits | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/compensation | NU-HRMS | Compensation | Pass | — | Not Tested | — | Not Tested
/contracts | NU-HRMS | HR Operations | Pass | ALLOWED | Not Tested | — | Not Tested
/dashboard | NU-HRMS | Dashboard | Fail | ALLOWED | Not Tested | — | Not Tested
/dashboards/executive | NU-HRMS | Dashboard | Pass | — | Not Tested | BLOCKED | Not Tested
/departments | NU-HRMS | People | Pass | ALLOWED | Not Tested | — | Not Tested
/employees | NU-HRMS | People | Pass | ALLOWED | Not Tested | — | Not Tested
/employees/directory | NU-HRMS | People | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/expenses | NU-HRMS | Expenses | Fail | ALLOWED | Not Tested | ALLOWED | Not Tested
/feedback360 | NU-Grow | Feedback360 | Pass | ALLOWED | Not Tested | — | Not Tested
/helpdesk | NU-HRMS | Helpdesk | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/leave | NU-HRMS | Leave | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/letters | NU-HRMS | Letters | Pass | ALLOWED | Not Tested | — | Not Tested
/loans | NU-HRMS | Loans | Pass | — | Not Tested | — | Not Tested
/me/attendance | NU-HRMS | My Space | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/me/dashboard | NU-HRMS | My Space | Pass | ALLOWED | Pass | ALLOWED | Not Tested
/me/documents | NU-HRMS | My Space | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/me/leaves | NU-HRMS | My Space | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/me/payslips | NU-HRMS | My Space | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/me/profile | NU-HRMS | My Space | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/nu-calendar | NU-HRMS | Calendar | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/nu-drive | NU-HRMS | Drive | Pass | ALLOWED | Not Tested | — | Not Tested
/nu-mail | NU-HRMS | Mail | Pass | — | Not Tested | — | Not Tested
/offboarding | NU-Hire | Offboarding | Pass | — | Not Tested | — | Not Tested
/okr | NU-Grow | OKR | Pass | ALLOWED | Not Tested | — | Not Tested
/onboarding | NU-Hire | Onboarding | Pass | — | Not Tested | — | Not Tested
/org-chart | NU-HRMS | People | Fail | ALLOWED | Not Tested | ALLOWED | Not Tested
/payroll | NU-HRMS | Payroll | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/performance | NU-Grow | Performance | Pass | ALLOWED | Fail | ALLOWED | Not Tested
/projects | NU-HRMS | Projects | Pass | ALLOWED | Not Tested | — | Not Tested
/recognition | NU-Grow | Recognition | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/recruitment | NU-Hire | Recruitment | Pass | — | Not Tested | — | Not Tested
/reports | NU-HRMS | Reports | Pass | — | Not Tested | — | Not Tested
/settings | NU-HRMS | Settings | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/statutory | NU-HRMS | Statutory | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/surveys | NU-Grow | Surveys | Pass | — | Not Tested | — | Not Tested
/tax | NU-HRMS | Tax | Pass | BLOCKED | Not Tested | BLOCKED | Not Tested
/training | NU-Grow | Training | Pass | ALLOWED | Not Tested | ALLOWED | Not Tested
/travel | NU-HRMS | Travel | Pass | — | Not Tested | — | Not Tested
/wellness | NU-Grow | Wellness | Pass | — | Not Tested | — | Not Tested