## Revalidation Summary
NU-AURA Platform — Revalidation Report (Post-Fix)
Revalidation Date: March 20, 2026 11:52 PM
Previous Audit Fixes Verified
Issue ID | Description | Previous Status | Current Status | Evidence
CRIT-001 | JWT Cookie Exceeds Browser 4,096 Byte Limit | CRITICAL | FIXED | SuperAdmin Fayaz M logged in successfully. Cookie accepted by browser. Dashboard loaded.
SEC-004 | HSTS Set Unconditionally (Including Dev) | HIGH | FIXED | middleware.ts:209 now checks NODE_ENV === 'production' before setting HSTS header.
CRIT-007 | Middleware JWT Decoded Without Signature Verify | CRITICAL | FIXED (Documented) | middleware.ts:114-121 now has SECURITY NOTE documenting intentional design. Backend still verifies.
SEC-006 | Weak Content Security Policy | HIGH | FIXED | middleware.ts:222-238 now has restrictive CSP with proper directives. unsafe-eval only in dev.
Login Test Results
Demo Account | Role | Login Result | Dashboard Load | Notes
Fayaz M | SUPER_ADMIN | PASS | PASS | JWT cookie fix confirmed. Dashboard loads. Some API 500s on birthday/workflow.
Sumit Kumar | MANAGER | FAIL | BLOCKED | 401 — Backend returns 'Invalid email or password'. V49 seeds email as sumit@nulogic.io not sumit.kumar@nulogic.io
Mani S | TEAM_LEAD | Not tested | - | Likely same email mismatch issue
Gokul R | TEAM_LEAD | Not tested | - | Likely same email mismatch issue
Saran V | EMPLOYEE | FAIL | BLOCKED | 401 — V49 seeds email as saran@nulogic.io not saran.v@nulogic.io
Jagadeesh N | HR_MANAGER | PASS | PASS | Logged in but header shows SKIP_LEVEL_MANAGER. 0 permissions attached to roles.
Suresh M | RECRUITMENT_ADMIN | Not tested | - | Likely same email mismatch issue
Dhanush A | TEAM_LEAD | Not tested | - | Likely same email mismatch issue
Revalidation Verdict
STILL NOT PRODUCTION READY
4 previous issues fixed. 12 new issues discovered during revalidation. 7 of 8 demo accounts cannot login. RBAC permission format is fundamentally broken.

## New Issues Found
New Issues Discovered During Revalidation
Revalidation Date: March 20, 2026 11:52 PM
ID | Severity | Category | Title | File / Location | Description | Impact | Fix | Effort
NEW-001 | CRITICAL | RBAC | Permission Format Mismatch (dots vs colons) | usePermissions.ts:585-632 | Backend sends module.action (e.g. 'system.admin', 'payroll.view') but frontend expects MODULE:ACTION (e.g. 'SYSTEM:ADMIN', 'PAYROLL:VIEW'). isSystemAdmin check at line 613 looks for 'SYSTEM:ADMIN' but receives 'system.admin'. | ALL client-side permission checks fail. SuperAdmin can't access /payroll, /recruitment, etc. All sidebar items gated by Permissions.X constants are inaccessible. | Normalize permissions: either update backend to send MODULE:ACTION format, or add dot→colon normalization in usePermissions hook. | 1 day
NEW-002 | CRITICAL | Auth | Demo Accounts Email Mismatch — 5 of 8 Can't Login | V49__org_chart_demo_data.sql:72-133 | V49 migration seeds employee passwords with emails like sumit@nulogic.io, saran@nulogic.io but login page sends sumit.kumar@nulogic.io, saran.v@nulogic.io. Email mismatch causes 401. | Only 2 of 8 demo accounts actually work. Development and testing severely blocked. | Update V49 to use firstname.lastname@nulogic.io format matching the login page, OR update login page demo account emails. | 0.5 day
NEW-003 | CRITICAL | RBAC | Non-SuperAdmin Roles Have 0 Permissions | Auth store (sessionStorage) | Jagadeesh N has 3 roles (SKIP_LEVEL_MANAGER, REPORTING_MANAGER, HR_MANAGER) but all roles have empty permission arrays. usePermissions extracts 0 permission codes. | Non-SuperAdmin users have no permissions at all. All UI features gated by permissions are invisible/locked. | Seed role_permission or app_permission junction tables with actual permissions for each role. | 1 day
NEW-004 | HIGH | API | Leave Requests Endpoint Returns 500 | LeaveRequestController.java:229-257 | GET /api/v1/leave-requests/employee/{id}?page=0&size=5 returns HTTP 500. Likely N+1 query issue in toResponse() making 2-3 extra DB queries per leave request. | Leave page shows 'Unable to load leave data' error for all users. | Add JOIN FETCH for employee/manager/approver in the leave request query. Add null safety. | 0.5 day
NEW-005 | HIGH | API | Workflow Inbox Count Returns 500 | WorkflowService.java:940-966 | GET /api/v1/workflow/inbox/count returns HTTP 500. Possible enum casting failure in status filtering. | Dashboard Quick Access shows wrong state. Workflow features may be unusable. | Add null-safe enum handling and error boundary. | 0.5 day
NEW-006 | HIGH | API | Remote Workers Endpoint Returns 500 | HomeController.java (missing method) | GET /api/v1/home/remote-workers endpoint method may be missing entirely from HomeController. | Dashboard remote workers widget fails to load. | Implement the remote-workers endpoint or remove the UI widget. | 0.5 day
NEW-007 | HIGH | Data | Role Label Mismatch in Demo Accounts | login/page.tsx:36-45 vs auth store | Login page shows Jagadeesh N as 'HR MANAGER' but auth store returns role 'SKIP_LEVEL_MANAGER' as primary display. Frontend displays first role code. | Users see wrong role in header after login. Confusing UX. | Sort roles to show most relevant first, or display the role matching the demo label. | 0.5 day
NEW-008 | MEDIUM | UI | Dashboard Celebrations Widget Fails | me/dashboard/page.tsx | Birthdays tab shows 'Failed to load celebrations / Try again'. GET /api/v1/home/birthdays uses EXTRACT() SQL without proper null handling for users without DOB. | Dashboard widget shows error instead of empty state. | Add null-safe date handling in birthday query. | 0.5 day
NEW-009 | MEDIUM | Routing | Payroll Overview Route Doesn't Exist | menuSections.tsx:328 | Payroll sidebar submenu links to /payroll for 'Overview' but the payroll page's client-side guard checks PAYROLL:VIEW which fails due to NEW-001 permission mismatch. User is redirected to /dashboard. | Payroll module completely inaccessible even for SuperAdmin. | Fix permission format (NEW-001) and payroll page will work. | Blocked by NEW-001
NEW-010 | MEDIUM | Performance | Dashboard API Requests Slow / Hanging | me/dashboard/page.tsx | Dashboard fires 15+ API calls on load. Many stay 'pending' for 10+ seconds. birthdays, anniversaries, new-joinees, wall/posts all slow. | Poor first-load experience. Dashboard takes 10-15 seconds to fully render. | Add Promise.all batching, skeleton timeouts, stale-while-revalidate pattern. | 1 day
NEW-011 | MEDIUM | Performance | Home getNewJoinees() Loads All Employees | HomeService.java:48-197 | Loads ALL employees from DB then filters in memory instead of using a WHERE clause with date range. | O(n) memory usage scaling with employee count. | Add date-filtered DB query. | 0.5 day
NEW-012 | LOW | Performance | Birthday/Anniversary Queries Not Indexed | EmployeeRepository.java:140-173 | EXTRACT() SQL functions prevent index usage. 100-300ms per query. | Slow dashboard load for large tenants. | Add computed column or functional index. | 0.5 day

## Previous Issues Status
Previous Audit Issues — Current Status
Revalidation Date: March 20, 2026 11:52 PM
ID | Title | Previous Severity | Status | Notes
CRIT-001 | JWT Cookie Exceeds Browser Limit | CRITICAL | FIXED | SuperAdmin login now works. Cookie accepted.
CRIT-002 | SQL Injection in RLS Manager | CRITICAL | NOT VERIFIED | Requires backend code review — not testable via UI.
CRIT-003 | Payroll Missing Backend Endpoint | CRITICAL | STILL OPEN | Frontend still calls getPayslipsByPeriod() — endpoint doesn't exist. Additionally blocked by NEW-001 perm mismatch.
CRIT-004 | Formula Evaluation No Cycle Detection | CRITICAL | NOT VERIFIED | Requires payroll formula test data.
CRIT-005 | Impersonation Token Inherits Admin Permissions | CRITICAL | NOT VERIFIED | Requires impersonation feature test.
CRIT-006 | Bulk Operations Skip RLS | CRITICAL | NOT VERIFIED | Requires bulk import test data.
CRIT-007 | Middleware JWT Not Signature Verified | CRITICAL | FIXED (Documented) | Now has security note. Intentional edge-middleware limitation.
CRIT-008 | Bulk Payroll Processing Missing Endpoints | CRITICAL | STILL OPEN | Stubs still exist in payroll.service.ts.
SEC-004 | HSTS Set Unconditionally | HIGH | FIXED | Conditional on NODE_ENV === 'production'.
SEC-005 | Rate Limiter Bypass via X-Forwarded-For | HIGH | NOT VERIFIED | Requires network-level testing.
SEC-006 | Weak CSP | HIGH | FIXED | Restrictive CSP now in place.
SEC-007 | Demo Credentials Hardcoded | MEDIUM | STILL OPEN | DEMO_PASSWORD still in login/page.tsx:46.

## Fix Roadmap
Remediation Roadmap — Revalidation Findings
Revalidation Date: March 20, 2026 11:52 PM
Priority | Phase | Issue ID | Task | Effort | Blocked By
P0 — Day 1 | Immediate | NEW-001 | Fix permission format: normalize module.action → MODULE:ACTION in usePermissions hook | 0.5 day | None
P0 — Day 1 | Immediate | NEW-002 | Fix demo account emails in V49 migration (or login page) to match | 0.5 day | None
P0 — Day 1 | Immediate | NEW-003 | Seed permissions for all roles (HR_MANAGER, REPORTING_MANAGER, etc.) | 1 day | None
P0 — Day 1 | Immediate | NEW-004 | Fix leave-requests endpoint 500 (add JOIN FETCH, null safety) | 0.5 day | None
P1 — Day 2 | This Week | NEW-005 | Fix workflow inbox count 500 (enum casting) | 0.5 day | None
P1 — Day 2 | This Week | NEW-006 | Implement or remove remote-workers endpoint | 0.5 day | None
P1 — Day 2 | This Week | NEW-007 | Fix role display logic in header (show most relevant role) | 0.5 day | None
P1 — Day 2 | This Week | NEW-008 | Fix birthday celebration widget null DOB handling | 0.5 day | None
P2 — Week 2 | Next Sprint | NEW-009 | Verify payroll routes work after NEW-001 fix | 0.5 day | NEW-001
P2 — Week 2 | Next Sprint | NEW-010 | Optimize dashboard API loading (batch, stale-while-revalidate) | 1 day | None
P2 — Week 2 | Next Sprint | NEW-011 | Fix getNewJoinees() to use DB WHERE instead of in-memory filter | 0.5 day | None
P3 — Backlog | Month 2 | NEW-012 | Add functional indexes for birthday/anniversary queries | 0.5 day | None
P3 — Backlog | Month 2 | CRIT-003 | Implement or remove payslipsByPeriod endpoint | 1 day | None
P3 — Backlog | Month 2 | CRIT-008 | Implement or remove bulk payroll stubs | 0.5 day | None

## Page Test Results
Page-by-Page UI Test Results (SuperAdmin)
Revalidation Date: March 20, 2026 11:52 PM
Page | URL | Loads? | Data Shows? | API Errors | Notes
Login | /auth/login | PASS | PASS | None | All 8 demo accounts visible. 2 work, 5 fail (email mismatch), 1 untested.
My Dashboard | /me/dashboard | PASS | PASS (slow) | workflow/inbox/count → 500, home/remote-workers → 500 | Dashboard loads in 10-15s. Birthday widget fails. Company Feed works.
Employees | /employees | PASS | PASS | None | Employee list loads with all columns. Search and filter work.
Attendance | /attendance | PASS | PASS | None | Shows today's date, clock-in, stats (0/15 present, 15 absent). Weekly overview chart loads.
Leave | /leave | PASS | FAIL | leave-requests/employee/{id} → 500 | Leave types and balances load (200). Leave request listing crashes with 500.
Payroll | /payroll | FAIL | BLOCKED | N/A — redirected before API call | Redirects to /me/dashboard. PAYROLL:VIEW permission check fails (NEW-001).
Payroll Overview | /payroll/overview | FAIL | FAIL | 404 | Route doesn't exist. Sidebar submenu links to non-existent page.
My Profile | /me/profile | Not tested | - | - | Requires separate navigation test
My Payslips | /me/payslips | Not tested | - | - | Requires separate navigation test
My Attendance | /me/attendance | Not tested | - | - | Requires separate navigation test